## Slide 1: Agile@Scale KPIs
High level overview of external KPIs

## Slide 2
Known Bugs
Release Rates
Technical Debt
Cycle Times
& Lead Time
Efficiency
Quality
We are a FTSE 250 company not a start-up. We have to show accountability across the group, these KPIs help fulfil this.
Notes: We are starting with four simple KPIs across teams, these focus on Efficiency and Quality. At this time we are leaving the Product KPIs to the product side of the business to agree.
We expect that these metrics are easily accessible and automated from JIRA and ServiceNow where required.
All four metrics relate to each other, a decrease in cycle times and an increase in defects indicates that we are building things faster but cutting corners which will affect us in the future.
It is the responsibilities of the Delivery Teams and Product Teams to ensure that these metrics are kept in line together.
Product teams need to prioritise Technical Debt and Defect items every sprint to ensure we improve our products from all angles and in turn will speed up their speed in delivery.
Teams can build upon these metrics if they want to externalise more and as the appetite grows by the business we may expand the required KPIs but we will endeavour to make them easy to surface and collate and as automated as possible for consistency across the group.
FTSE 250: Consisting of the 101st to the 350th largest companies listed on the London Stock Exchange. They are mainly investment trusts, and means we have heavily audited and have many share holders. We are held accountable for everything we do, with these KPIs we are trying to reduce this burden on teams and delivery team members.

## Slide 3: Cycle Times & Lead Time (Story Level) + Release Rates
Lead Time
Idea
Hands of the Customer
Elaboration
From analysis to ready for development
Build & Validate
From ready for development to ready for environments
Integration
From ready for environments to Hands of the Customer
Product
Tech Delivery
Tech Ops
As we grow our Product maturity Elaboration will merge in to become one cycle time
As we grow our DevOps culture Build & Validate and Integration will be merged
Teams should only be measured on what they can control
Production Support
How many releases?
Stories should be broken down from an
Epic/Feature close to the time of delivery.
Notes: Business Cycle time has been referenced by people within the business, in general this is known as the Lead time how long does it take from Idea to Hands of the Customer.
Cycle times are within this and is the time from when work begins to when it completes.
We have separated out our cycle times in too three distinct sections:
Elaboration
Build & Validate
Integration
Elaboration
This is where the product team and business analysts work on the epics / stories and get the requirements and acceptance criteria together and then work with the teams to understand how to break it down into workable chunks. Elaboration only starts when the BA/PO start the analysis of the work, so it can sit on the backlog and just increase the Lead Time only.
Build & Validate
This is the technology delivery teams picking up the work and getting it built and tested locally. Something that they can control, some areas of the business don’t have as many blockers in environments as others and maybe able to push to integration environments and pre-prods with out issues. We are trying to pick the lowest bar that a team can control to be the basis of the cycle times.
This is to indicate that the team have everything they needed, are able to build it and test it and demo locally to their stakeholders.
Integration
This is where some teams struggle in their flow as they have to raise a release request which has to be co-ordinated with others and will delay the teams actual cycle times.
Separating it out means that we have metrics to show that when it’s moved to a more DevOps culture the teams can do this and move down the line with ease.
Usage
On teams boards they may have statuses that cover these overlapping areas as they can indeed control their environments. What we’re trying to do is get everything to a level that is comparable cross teams in channels.
Over time we expect that we collapse these cycles times in too two and then finally in to one as the teams before more fluent in agile.
In addition with Release Rates how often are our teams releasing we may need to have more narrative around these numbers as it has been seen in other transformations out side of William Hill that the release rate between Waterfall and Agile is the same. The difference is the size of the release, Waterfall one big bang release followed by patch releases and agile continuous small releases.

## Slide 4: Technical Debt & Known Bugs
  Technical Debt
This is an open honest account from teams about areas of their product that they know isn’t strategic or in support.
These are items that will slow the team down in the future and should be prioritised in the sprint planning / refinement sessions to ensure they are resolved.
  Known Bugs
These are the number bugs that we know about but haven’t yet serviced. These need also be prioritised by the product team and brought to sprint planning sessions.
Customer and Service impacting issues like P1 and P2 would be resolved immediately and this wouldn’t be captured in this metric. These would come in to service availability metrics.
These metrics keep in line the efficiency metrics.
If our cycle time reduce and our release rates increase but our Technical Debt & Known Bugs and Service Availability raise then we have an issue to resolve.
It’s the teams responsibility to ensure that all metrics are in line.
Notes: Technical Debt has to be clearly defined and currently the understand is the usage of non-tactical solutions / tools / programming languages.
This may for example be a version of a certain language that is no longer supported like Java 6 for example.
Teams should be calling these out, as long as there is a narrative to go with it, the understanding is there. As teams work on different areas of their products they will in the course of the work identify technical debt they didn’t know was there. We’d rather have this surfaced so that Architecture teams and Heads of Technology to work to help reduce these areas that may become support issues in the future.
Known Defects will come from two sources, one is known issues in production that have been raised via ServiceNow and placed on the products backlog. The other is that while we are developing new features / stories a defect is discovered but the Product Owner or BA is happy to go to production with it and fix it later.
These should all be pulled from JIRA, and for this to work consistently we need to teams to work in similar ways where possible.
Teams have to remember that we are a FTSE 250 company and have to be accountable and we want to make this reporting as easy as possible and reduce the over head in these areas.

## Slide 5: Appendix A
Example workflows to support the metrics
Notes: What follows are some ideas around workflows that teams could use in their work.
A worked example is being created to show how this can work for the team.

## Slide 6: Initial Example Workflow – Stories
Open (Not part of the Cycle Time)
In Analysis
Waiting for Dev & QA Analysis
In Dev & QA Analysis
Ready for Development
Elaborate (Product Team)
Build & Validate (Technology Team)
Integrate (OPS Team)
Ready for Development
In Implementation
Waiting for Implementation
3 Amigos
Waiting for Review
In Review
In Validation
Waiting for Integration
Waiting for Validation
Waiting for Integration
Scheduled for Production
Done
In Integration Test
Waiting for Production
Lead Time (Business Cycle Time)
Sprint Starts
Sprint Ends where the team feels is the right place for them
William Hill Default Definition of Done
Definition of Ready
Notes: Elaborate
We want to know how long it’s taking to get stuff ready for Definition of Ready we also want to ensure that it’s key that the team is involved as early as possible hence the statues at this level. Although it’s not in sprint it’s work the team need to do, and not everything will be towards this current sprint but we need to have an eye on the future.
Build & Validate
This is how long it takes us to build & test stuff and ready for production.
We have 3 Amigos here as a status to help ensure that Devs & QA work together throughout the lifetime of the story
Integrate
How long does it take us to get stuff from being ready for development into Production

## Slide 7: Workflow – Sub Tasks
In-Sprint (Technology Team)
Waiting for Build
In Build
Done
Notes: Sub tasks should be short lived and run through as quick as possible and normally done in hours not days or points

## Slide 8: Workflow – User Story Bug (Sub-Task) Issues found during development
In-Sprint (Technology Team)
3 Amigos
In Build
Waiting for Build
In Validation
Done
Waiting for Validation
Notes: When an issue is found with a story during development it’s right that the QA team raise a defect (If need be, think about the time it takes to raise to the time it takes to fix)
We should also discuss the defect with the PO/BA and if they feel that it needs to be fixed we fix it, else we change it to a backlog defect for future refinement and planning.
This would be a known issue in the releases we’re making and may agree that we highlight this?

## Slide 9: Workflow – Risks & Issues TBC
Identify
Open
Assess
Create Mitigation Plan
Done
Implementation in Progress
Close
No Action Needed
Reopen
Reassess
Notes: We want our Risk & Issues to be living items not just in a static wiki page / excel we want to see them and visualise them with other teams and channels if we need to.
This will help find common themes but also help the teams understand what they need to tackle to make them go faster.

## Slide 10: Workflow – Tech Debt TBC
Identify
Open
Assess
Create Mitigation Plan
Done
Implementation in Progress
Close
No Action Needed
Reopen
Reassess
Notes: It’s important that when we decide to use a tactical solution, cut a corner etc. that it is tracked.
Again themes can be raised against this and the Architecture teams will have a view of what’s important to them and understand issues that may be a cause for concern.

## Slide 11: Appendix B
Timescale for the initial rollout

## Slide 12: Timelines
  Weeks Commencing
  23rd July - Done
Review the Metrics with Senior Management Teams across Digital/Trading/Retail.
  30th July – In Progress – Delayed 1 week
Work with selected teams (Digital - Bonus Platform / Retail – SSBT / Trading - Feature Team 3) To get workflows in shape that can track our required metrics and ensure consistency.
Look at JIRA dashboards for the teams to help them improve.
  6th August / 13th August – Pushed back 1 week
Start of a teams sprint, to get them on the new workflow & finish board configuration. Start tracking the data consistently.
  10th September – Expected to be towards end of September
We have at least 2 sprints of data to generate the start of the reports and ensure we’re happy with the quality and can stand by the data that is generated.
Q4 rollout across all teams